## Prod Backlog Gradebook
Product Backlog Items | Initial Estimate | Adjustment Factor | Adjusted Estimate | Work Remaining Until Completion
Title |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Create courses | 1 | 0.2 | 1.2 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enter a name, code, description, and dates/times course meets for each course
View and delete courses | 2 | 0.2 | 2.4 | 3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Add assignments to a course | 1 | 0.2 | 1.2 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enter name, due date, possible points for each assignment
View and delete assignments | 2 | 0.2 | 2.4 | 3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Add students to a course | 1 | 0.2 | 1.2 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enter a first and last name for each student
View and delete students | 2 | 0.2 | 2.4 | 3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sprint-1 | 9 | 0.2 | 10.8 | 14.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create a gradebook for a course | 5 | 0.2 | 6 | 4.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Assign a grade to each student for each assignment in a course
View each students assigned grades for each assignment
Provide a chronological view of all of assignments that are due | 2 | 0.2 | 2.4 | 5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sprint-2 | 7 | 0.2 | 8.4 | 10.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Provide easy access to all activities | 1 | 0.2 | 1.2 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Provide necessary data validation on input data | 1 | 0.2 | 1.2 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Give consistent look and feel to all activities | 1 | 0.2 | 1.2 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Make all messages easy to understand | 1 | 0.2 | 1.2 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Filter view of courses by name, code, or description | 2 | 0.2 | 2.4 | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sprint-3 | 6 | 0.2 | 7.2 | 7.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Release-1 |  |  |  | 31.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0